## old-fashioned.csv
Hierarchy | Title | Description | Project | Releases | Teams | Members | Sprints | Earliest start | Target start | Scheduled start | Due date | Target end | Scheduled end | Story Points | Original Story Points | Parent | Labels | Components | Themes | Issue key | Issue status | Epic/Theme | Progress (%) | Progress completed | Progress remaining
Initative | Enhancing Insight Functionalities | This initiative will contain following features: * PPT export * PPT and Excel Export of Collections * Sharing Favorites and Collections * Localisation of the Insight UI * etc. i.e. improving client user experience. | Market Reporting | Old Fashioned, Gin & Tonic | MR BI Team Team, MR PO/PD Team Team, MR PS Team Team | Alexander Firsching, Volko Christ | MR PS Team Team: Sprint 4, MR BI Team Team: Sprint 4 |  |  | 28. August 2018 |  |  | 10. September 2018 | 18 | [5 empty] | NEO-1323 | Open |  | 0 | 0 | 18
Feature | Release Notes in Insight | The goal of this feature is to provide release notes (features and/or functions information) in the Insight directly. At the moment this infomation is being communicated via CCR Community to the local team, who later are in chanrge of the communication to the clients. Benefit: Improve client satisfactioon Acceptence Criteria: * show in the insight that there are new features/functions available * provide a file where the description can be added (the text should be formated properly,e.g. font size.) * Similar behaviour as it is available for newly loaded elements in the product hierarchy. This means if the user already looked at the new funtions, then this information should not pop-up anymore. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Enhancing Insight Functionalities | RS_RN_yes | Conditioned Feature Backlog, Product Offering / Product Design |  | NEO-1325 | Open |  | 0 | 0 | 0
Epic | Introduce Notifications to RetailScout | As a User of RS I want to know if there are new features in the interface, so that I can try them out. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Release Notes in Insight |  | Product Offering / Product Design |  | NEO-2558 | Open |  | 0 | 0 | 0
Story | Is getting data from Confluence feasible? | Since the Release Notes will be released on Confluence, it would be practical to get the information for the Release Notes in Retail Scout directly from there. This spike should gives us insights into: * How much effort will we have using the API? [https://developer.atlassian.com/server/confluence/confluence-rest-api-examples/] * What kind of technical challenges will we have? * What kind of data validation challenges will we have? * etc... If there are severe doubts of whether we should use Confluence, then this Spike should also contain possible better alternatives. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Introduce Notifications to RetailScout |  | Product Offering / Product Design |  | NEO-2559 | Open |  | 0 | 0 | 0
Feature | Stretch Objective: Improve PPT export - vertical pagination | At the moment when using an powerpoint export functionality, each exported report will be fitted to a powerpoint slide. In some case when the report is too large for one slide, a pagination (cutting in to several pictures) is required, so the that the information provided by the report can be read easily. Benefit: improve customer satisfaction Acceptence Criteria: * export report which exceeds (vertically) the acceptable powerpoint slide * the report should be cut into several images, thereby totals and legend need to be repeated, so that the report's context is not lost. * in case of grouping - the grouping chould not be split over several slides | Market Reporting | Gin & Tonic, Old Fashioned | [11 empty] | Enhancing Insight Functionalities | RS_RN_yes | Conditioned Feature Backlog, Product Offering / Product Design |  | NEO-1888 | Open |  | 0 | 0 | 0
Feature | Enable export of the tables (116/101) report | Support powerpoint export for tables.At the momet suported only for charts. Benefit: * improve customer satisfaction Acceptance Criteria: * Report 101 and 116 can exported to powerpoint | Market Reporting | Old Fashioned | MR BI Team Team, MR PO/PD Team Team, MR PS Team Team | Alexander Firsching, Volko Christ | MR PS Team Team: Sprint 4, MR BI Team Team: Sprint 4 |  |  | 28. August 2018 |  |  | 10. September 2018 | 18 |  | Enhancing Insight Functionalities | RS_RN_yes | Conditioned Feature Backlog, Product Offering / Product Design |  | NEO-1159 | Open |  | 0 | 0 | 18
Epic | PPT Export tables first draft |  | Market Reporting | Old Fashioned | MR BI Team Team, MR PO/PD Team Team, MR PS Team Team | Alexander Firsching, Volko Christ | MR PS Team Team: Sprint 4, MR BI Team Team: Sprint 4 |  |  | 28. August 2018 |  |  | 10. September 2018 | 18 |  | Enable export of the tables (116/101) report |  | Product Offering / Product Design |  | NEO-1209 | Open |  | 0 | 0 | 18
Story | Integrate Excel Export into Export Service | As a software developer I want to separate the Excel Export from the Query Service into an own Export Service, so that the maintainability is easier and there is a clear separation of concerns. +Background:+ Until now, the Excel Export is integrated into the Query Service. Since there is also the Powerpoint Export, it makes more sense to integrate both into an own Export Service. This enhances maintainability of the code. First setup and building skeleton of the Export Service is included in this User Story. Refactoring is also included in this story. | Market Reporting | Old Fashioned | MR PS Team Team |  | MR PS Team Team: Sprint 4 |  |  | 28. August 2018 |  |  | 10. September 2018 | 13 |  | PPT Export tables first draft |  | Product Offering / Product Design |  | NEO-1063 | Open |  | 0 | 0 | 13
Sub-Task | Integrate new File-Export-Service in the Frontend | Connect to the new file-export service when exporting Excel files. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Integrate Excel Export into Export Service |  | Product Offering / Product Design |  | NEO-1195 | Open |  | 0 | 0 | 0
Sub-Task | Set up Platinum Cloud Server for Export Service | Set up a Platinum Cloud Server for the FileExportService Enable Deployment Add Monitoring to the Server | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Integrate Excel Export into Export Service | DevOps | Product Offering / Product Design |  | NEO-1391 | Open |  | 0 | 0 | 0
Story | Integrate Powerpoint Export into Export Service | As a software developer I want to separate the Powerpoint Export from the Query Service into an own Export Service, so that the maintainability is easier and there is a clear separation of concerns. +Background:+ Until now, the Powerpoint Export is integrated into the Query Service. Since there is also the Excel Export, it makes more sense to integrate both into an own Export Service. This enhances maintainability of the code. | Market Reporting | Old Fashioned | MR BI Team Team | Alexander Firsching, Volko Christ | MR BI Team Team: Sprint 4 |  |  | 28. August 2018 |  |  | 10. September 2018 | 5 |  | PPT Export tables first draft |  | Product Offering / Product Design |  | NEO-1062 | Open |  | 0 | 0 | 5
Story | Enable PPT export of tables as one large picture |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | PPT Export tables first draft |  | Product Offering / Product Design |  | NEO-1768 | Open |  | 0 | 0 | 0
Story | Enable PPT export of tables WYSIWYG | As a Retailer, I want to export the 116 Report directly into Powerpoint as one large picture, so that can directly work with it. +Acceptance Criteria:+ * tbd | Market Reporting | Old Fashioned | MR PO/PD Team Team |  |  |  |  | 14. August 2018 |  |  | 24. September 2018 |  |  | PPT Export tables first draft |  | Product Offering / Product Design |  | NEO-454 | Open |  | 0 | 0 | 0
Epic | Enable PPT export of tables with pagination |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Enable export of the tables (116/101) report |  | Product Offering / Product Design |  | NEO-1769 | Open |  | 0 | 0 | 0
Feature | Provide direct access to Collections | List and provide access to the last 10 used collections on Landing Page. Benefit: improve client satisfaction by easier access to the colletions. Acceptance Criteria: * add separate accordion on LP * list collections | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Enhancing Insight Functionalities | RS_RN_yes | Conditioned Feature Backlog, Product Offering / Product Design |  | NEO-1569 | Open |  | 0 | 0 | 0
Initative | RetailScout scales to 1200 retailers |  | Market Reporting | Old Fashioned, Gin & Tonic | [5 empty] | 14. August 2018 |  |  | 24. September 2018 | [6 empty] | NEO-287 | In Progress |  | 0 | 0 | 0
Feature | Re-use panelmarket figures for all clients in one country | Example: for RU PM is being calculated 24 times, although the figures are exactly the same for all retailers in RU. calculation times for RU: Retailer + CH-ME: 28min PM + CH: 170min estimated time reduction ca 40% The goal is to identify identical panelmarket (can it be also done for the CH?) in one country are share the figures for all retailers. Benefits: - reduce HW costs, due reduced data volume | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | RetailScout scales to 1200 retailers | RS_RN_yes | BI Layer, Conditioned Feature Backlog, Product Offering / Product Design, Product Subscription, Reporting Data Preparation |  | NEO-1969 | Open |  | 0 | 0 | 0
Feature | Reduce time needed to process the data (FTP->AS) | Currently the time needed to process data from FTP to AWS can take up to 26 hours: 13 h waiting time in queue 4 h check if new data is available 7 h pre-processing data At the moment the requirement is to process the data within 4h. Benefit: improve customer satisfaction by delievering data in time Business Value: 5 - high Acceptance Criteria: * evaluate the time needed to preprocess the data, come up with the possible solutions to reduce the time * Document the solutions, align with architect * implement the solution | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | RetailScout scales to 1200 retailers | RS_RN_no | Product Subscription |  | NEO-2459 | Open |  | 0 | 0 | 0
Feature | **Scale up RS from 200 to 400 clients (Wave 4) | Currenty we have rolled out 130 retailers, in the next month we expect set up and rollout of ca. 300 additional retailers. In order to enable efficient rollout of further clients and improve our cost structure we need: * set up and configure data marts - Migrate PS servers in cloud - provide manual for NCDM - support of the client rollout Benefit: enable savings and increase dev efficiency Acceptance Critearia: * NL DataMarts required for rollout of the clients has been setup * PS (preprocessing) instances are migrated to AWS cloude * NCDM manual is in place * manual weekly update of the content changes is done | Market Reporting | Gin & Tonic, Old Fashioned | [11 empty] | RetailScout scales to 1200 retailers | RS_RN_no | BI Layer, Conditioned Feature Backlog, Product Subscription, Reporting Data Preparation |  | NEO-833 | In Progress |  | 0 | 0 | 0
Feature | Enable additional exclusivity handling "Agg to TB&Excl" to rollout furhter countries | In order to be able to rollout AU & NZ retailers we need to support "Agg to TB&Excl." Exclusivity Handling on Item Level. Benefit: we will be able to rollout countries like AU & NZ Enable savings Acceptance Criteria: * Items with "agg to TB&Excl" handling mode are displayed as a single tag in the All Hitlists * TB&Excl are excluded from the Top X Calculation and added to Others * TB&Excl are shown in a separate line in hitlists. * TB&Excl figures reflect Feature and/or PCL filter settings. | Market Reporting | Gin & Tonic, Old Fashioned | [11 empty] | RetailScout scales to 1200 retailers | RS_RN_yes | Conditioned Feature Backlog, Product Offering / Product Design, Reporting Data Preparation |  | NEO-1211 | In Progress |  | 0 | 0 | 0
Feature | Migrate MediaMarkt and Saturn clients to NeoLite | At the moment MM and Saturn are delivered via STC. The main challenge is that users that need access to both clients cannot not be granted with such permossion due to current system limitation. current solution looks like this: !image-2018-06-08-11-46-22-747.png! Benefit: reduce HW load improve ops efficiency Acceptance Criteria: Media Markt and Saturn can be delivered via NEO Lite the clients can access both Retailers in insight. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | RetailScout scales to 1200 retailers | RS_RN_yes | Conditioned Feature Backlog, Product Subscription |  | NEO-2134 | Open |  | 0 | 0 | 0
Initative | Enhancing RetailScout Content | This initiative will include following features: * Fair Share report * Running Report * 3 Rolling Months * Enhanced Highlighting * etc. i.e. extending the content of the RetailScout. | Market Reporting | Old Fashioned, Gin & Tonic | [5 empty] | 14. August 2018 |  |  | 24. September 2018 | [6 empty] | NEO-309 | In Progress |  | 0 | 0 | 0
Feature | Fair Share | Provide new module "Fair Share" Benefit: improve customer satisfaction Business Value: 5 Acceptance Criteria: * Report is available on LP ( including tooltip) * Calculation of new KPIs is done * Sector, category, PGs and Brands, no items can be added in Side Heading * Provide new visualisation - first step left part, then right part * Provide new tooltips to describe the figures on the chart * Excel, PPT exports shall be supported * Favorites and Collections shall be supported | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Enhancing RetailScout Content | RS_RN_yes | Conditioned Feature Backlog, Product Offering / Product Design, Unconditioned Feature Backlog |  | NEO-274 | Open |  | 0 | 0 | 0
Feature | Replace full year by 3 rolling months | Replace FY with 3 rolling month (incl. PYP). Benefit: 1. significant value for the users, improve customer satisfaction https://jira.gfk.com/browse/CCR-156 Clients have requested that a quarterly view be available within the tool. We would like to remove the current "Full Year" view, and replace it with "Last 3 Months" which would be effectively a rolling quarter. This would be valid in all modules where we currently offer the Full Year view. 2. Removal of FY will reduce data volume, load time and HW costs: ¦ ¦Incl. FY¦Ohne FY¦Einsparung (ca.)¦ ¦PG – Level¦593 sec¦480 sec¦20%¦ ¦Brand - Level¦1562 sec¦717 sec¦54%¦ Acceptance Criteria: FY has been removed 3 rolling month (last 3 month) and PYP can be selected by the user in the insight. PP is OoS (was exluded during PI Plannig) | Market Reporting | Gin & Tonic, Old Fashioned | [11 empty] | Enhancing RetailScout Content | R5(G&T), RS_RN_yes | Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository, Product Offering / Product Design, Product Subscription, Reporting Data Preparation |  | NEO-766 | In Progress |  | 0 | 0 | 0
Initative | Sustainable and Maintainable Software Solution |  | Market Reporting | Old Fashioned, Gin & Tonic | MR BI Team Team, MR PS Team Team | Fotini Gonatidi | MR PS Team Team: Sprint 5 |  |  | 14. August 2018 |  |  | 24. September 2018 | 16 | [5 empty] | NEO-310 | In Progress |  | 31 | 5 | 11
Feature | Implement Monitoring - follow up | this is a follow up Feature targeting to implement the solution which was investigated in G&T PI. Benefit: improve development efficiency Acceptance Criteria: | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | BI Layer, Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository, Product Offering / Product Design, Product Subscription, Reporting Data Confirmation, Reporting Data Preparation |  | NEO-2278 | Open |  | 0 | 0 | 0
Epic | Implement Monitoring KPIs for KDS RR | In Sprint 10 of Gin&Tonic the members of the the KDS/RR team have identified KPIs, which have to be monitored in order to ensure that all component-relevant systems are up and running. Acceptance Criteria: - Monitoring/Notification for KPIs X,Y, Z is implemented - .... | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Implement Monitoring - follow up |  | Key Dimension Spec / Reporting Repository |  | NEO-2591 | Open |  | 0 | 0 | 0
Story | Implement Monitoring KPIs for KDS/RR | As a member of the KDS/RR-team a monitoring system must provide information if key systems of KDS/RR are up and running or alarm immediately or not. TBD with architect - which monitoring framework has to be used. monitoring KPIs are depend on analysis-US NEO-1849 | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Implement Monitoring KPIs for KDS RR |  | Key Dimension Spec / Reporting Repository |  | NEO-2592 | Open |  | 0 | 0 | 0
Feature | Clean up AS clusters to enable efficient data storage | Currently available estimation implies that the capacity of 1 cluster with 5 nodes is sufficient for 50 clients. at the moment we have ca. 110 clients with at least one shipped delivery and have to set up a 4th cluster. In general we have comitted to have max. 3 deliveries per client. This means all old deliveries (e.g. from 2017, or derlivered by ST-C) has to be deleted. Unshipped Deliveries has to be deleted as well. Potential Benefit: * reducing HW costs Acceptance Criteria: * double check capacity of the 1 cluster / 5 nodes - it could be possible that the estimation is not valid anymore. * evaluate and document the todos to clean up the clusters * conduct the clean up, impelent automatic process. * removed from scope: automatic deletion process is in place (incl. test coverage) | Market Reporting | Gin & Tonic, Old Fashioned | [11 empty] | Sustainable and Maintainable Software Solution | RS_RN_no | Conditioned Feature Backlog, Product Offering / Product Design, Product Subscription |  | NEO-1164 | In Progress |  | 0 | 0 | 0
Feature | Evaluate and document KPIs needed to be monitored | the goal is to evaluate and to define per sub-domain (component) which KPIs / Checks need to be conducted. oos: implementation Acceptance Criteria: * per component team: discuss and document which checks are * think about possible solutions and document them * double check with architects and other teams | Market Reporting | Gin & Tonic, Old Fashioned | MR BI Team Team |  |  |  |  | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | BI Layer, Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository, Product Offering / Product Design, Product Subscription, Reporting Data Confirmation, Reporting Data Preparation |  | NEO-843 | In Progress |  | 0 | 0 | 0
Epic | Implement Monitoring for BI | This epic is to introduce the monitoring to avoid manual effort we are spending there and also to get some metrics on performance and so on.. All the details about the KPI's and the solution approach will be documented under the confluence page https://confluence.gfk.com/display/S2/BI%3A+Monitoring | Market Reporting | Gin & Tonic, Old Fashioned | MR BI Team Team | [10 empty] | Evaluate and document KPIs needed to be monitored |  | BI Layer |  | NEO-370 | In Progress |  | 0 | 0 | 0
Epic | Evaluate Monitoring for BI | Currently there is no monitoring in place for the BI components. Often the issues are solved after they raise. Through monitoring we can better maintain the components and also evaluate the resources utilization. As part of this epic we would like to * Gather the KPI's that needs to be monitored for all BI components * Source of information for these KPI's * Missing log/source of information for any of the KPI's * Possible solutions to implement a centralized dashboard * Align and discuss with architects to have a common approach for whole NEO *Some examples:* *KPI's:* * JEE Status per comptype/DataMart * Job Monitoring * JEEJobTools (Monitoring, Analysing, reenqueue * Queue length * Waiting time * Jobs processed per hour/day *Server/Machine:* * CPU load * Memory usage *Availability:* * **Applications in different environments up and running * Response time for the URL.. Findings would be updated at [https://confluence.gfk.com/display/S2/Monitoring+KPI%27s+for+BI+Components] | Market Reporting | Gin & Tonic, Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Evaluate and document KPIs needed to be monitored |  | BI Layer |  | NEO-1657 | In Progress |  | 0 | 0 | 0
Feature | Optimize BI Node Configuration | As the Market Reporting team we want to optimize the BI Node configuration to save costs, reduce the amount of configurations, reduce the overall export/report execution time and support a effective untilization of datamarts. *Business Value*: 2 *Acceptance Criteria* * overall export/report execution time improved significantly * overall export/report execution time improvment documented and communicated * cost savings realized, documented and communciated * effective utilization of datamarts documented, proved and communciated * amount of configuration reduced, documented and communciated * BI subsystem tested end-to-end | Market Reporting | Old Fashioned, Gin & Tonic | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | BI Layer, Conditioned Feature Backlog |  | NEO-2448 | In Progress |  | 0 | 0 | 0
Epic | Increase the Number parallel exports on a BI Node to maximize the datamart utilization | Currently to handle exports use case each BI Node is set up with 8 exports slots(8 App server instances), 4 DB connections and 8 DOP. The number of export slots have to be increased on the BI machines to utilize the datamarts efficiently. The export slots should be in proportion to the size of the datamart. | Market Reporting | Gin & Tonic, Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Optimize BI Node Configuration |  | BI Layer |  | NEO-2405 | In Progress |  | 0 | 0 | 0
Epic | BI Node to use multiple export slots instead of multiple app server instances | Through this epic we would like evaluate case 4 of the BI Node set up mentioned in the confluence page [https://confluence.gfk.com/display/S2/01.+Possible+Solutions+-+BI+Nodes+Move+to+Platinum+Cloud.] If the evaluation in the POC machine works fine then we have to change the set up in all the environments that are created in the platinum cloud. Below * CPU usage of datamarts * Memory usage on the BI Node VM's set up in platinum cloud Accordingly we should modify our automated config tool and deployment tool to support this new configuration. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Optimize BI Node Configuration |  | BI Layer |  | NEO-1525 | Open |  | 0 | 0 | 0
Feature | Evaluation Meta Data Model Decoupling from StarTrack | As the Market Reporitng team, we want decouple our needed meta data from the StarTrack system to be independent from StarTrack releases, changes and resources. For this reason we want to evaluate what is possible and what is needed to do this decoupling step. *acceptance criteria* * all relevant meta data model dependencies to StarTrack checked and documented * possible solutions analysed and documented * decision for one alternative was taken and documented * further features to implement this decision discussed with the team and the technical lead * feature for implementation added to the backlog | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | BI Layer, Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository, Reporting Data Preparation |  | NEO-288 | Open |  | 0 | 0 | 0
Feature | Job Execution Environment (JEE) Infrastructure Decoupling from StarTrack | As the BI team, we want decouple our Job Execution Environment (JEE) from the StarTrack system infrastructure so that we are independend from StarTrack releases, changes, resources. Additionally we want to check if we can replace the self developed solution JEE by a standard job execution solution. *Acceptance Criteria * Anyalse alternative solutions * If JEE remains ** Market Reporting JEE infrastructure provided ** Market Reporting JEE infrastructure configured ** Market Reporting JEE infrastructure tested ** Market Reporting JEE infrastructure up and running * Otherwise ** Standard system configured, tested, up and running | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | BI Layer, Conditioned Feature Backlog |  | NEO-1554 | Open |  | 0 | 0 | 0
Feature | Replace MDM master data load by DWH master data load | As the Reporting Repository team we want to replace our existing MDM master data load solution by a more sustainable one and load all master data from the StarTrack DWH schema. Reason for that is to get the more consistent data which are available in StarTrack DWH and get rid of StarTrack internal dependencies and inconsistencies between the MDM and the DWH. *Acceptance Criteria* * all MDM date are replaced by the DWH data * all data will be loaded via an DWH interface (standard database interface) * no MDM interface will be used anymore * the data load pipeline is tested and documented *Business Value* 4 | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository, StarTrack |  | NEO-2593 | Open |  | 0 | 0 | 0
Feature | Reporting Repository API is downward compatible | As the Reporting Repository team we want to offer downward compatible APIs. *Acceptance Criteria* * all API versions are fully downward compatible * API are tested and tests passed * API documentation adjusted *Value* * better maintainablility and better usage of the APIs * cost reductions by the improved maintainability *Business Value* 3 | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository |  | NEO-2541 | Open |  | 0 | 0 | 0
Epic | Reporting Repository API is downward compatible |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Reporting Repository API is downward compatible | API | Key Dimension Spec / Reporting Repository |  | NEO-2576 | Open |  | 0 | 0 | 0
Story | RR: Standardize Version 2 RR API to include existing Version 1 API | As an API consumer from RDC Team, I would like the RR Version 2 (V2) API to also include the existing Version 1 (V1) API so that RDC project will only need to use the V2 API and not both V1 and V2. Acceptance Criteria: * Standardize RR V2 API to include below API that exists in V1 previously with some minor changes: ** /v1/hierarchy/dimension ** /v1/hierarchies/\{dimensionId}/\{referenceSystemId} *** to decide whether \{referenceSystemId} is still needed because it is always refer to "Reporting Repository" currently with Id: 11. ** /v1/hierarchies/\{dimensionId}/\{referenceSystemId}/\{referenceId} *** to decide whether \{referenceSystemId} is still needed because it is always refer to "Reporting Repository" currently with Id: 11. ** /v1/hierarchies/\{hierarchyId}/contexts *** context should no longer be used in v2; use \{hierarchyVersionId} instead. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Reporting Repository API is downward compatible |  | Key Dimension Spec / Reporting Repository |  | NEO-2224 | Open |  | 0 | 0 | 0
Feature | Replace Aerospike client copy in QueryService with library import | As the offering team we want to replace the copied and GfK specific adjusted AeroSpike client by the standard AeroSpike library. Furthermore we want (and we really want to) to use the most recent AerospikeClient version. *Acceptance Criteria* * Functionality that was previously added to the AerospikeClient sourcecode is still provided by the service. * The QueryService no longer contains a copy of the AerospikeClient sourcecode, but uses a library import instead. * The AerospikeServer has a version supporting the imported AerospikeClient version. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | Conditioned Feature Backlog, Product Offering / Product Design |  | NEO-2340 | Open |  | 0 | 0 | 0
Epic | Replace Aerospike sourcecode in QueryService with library import | Replace inserted old library code with library in the QueryService. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Replace Aerospike client copy in QueryService with library import |  | Product Offering / Product Design |  | NEO-2341 | Open |  | 0 | 0 | 0
Story | Replace Aerospike sourcecode in QueryService with library import | The QueryServices currently uses a copy of the AerospikeClient sourcecode from Oktober 2015. In proper form, it would instead simply import the AerospikeClient library as dependancy via gradle. Changing this is not trivial, since the sourcecode contains manual changed and minor additional functions, that first need to be refactored out of the AerospikeClient and into the service, before the AerospikeClient sourcecode can be removed in favor of a library import. Furthermore, if we want (and we really want to) to use the most recent AerospikeClient version, {color:red}*this may make it necessary to update the used version of our AerospikeServers as well*{color}. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Replace Aerospike sourcecode in QueryService with library import |  | Product Offering / Product Design |  | NEO-2332 | Open |  | 0 | 0 | 0
Feature | Upgrade WildFly 12 | Currently we use WildFly 10.1 which is quite outdated Benefit: * Potential improvements can help reducing complexity and machine provisioning effort (e.g WildFly may replace Apache SSL certificate termination) * compliant with technology map Major Effort on DevOps side: * there will be effort to change Puppet scripts * approx. 4 servers need to be adjusted per non-prod environment, 8 server for prod Out of scope of this meeting are: * replacement of Apache server * replacement of Tomcat servers * replacement of Tomcat security plugin more information, please see: https://confluence.gfk.com/display/S2/2018-03-28+WildFly+12+Upgrade | Market Reporting | Old Fashioned | MR BI Team Team, MR PS Team Team | Fotini Gonatidi | MR PS Team Team: Sprint 5 |  |  | 14. August 2018 |  |  | 24. September 2018 | 16 |  | Sustainable and Maintainable Software Solution | RS_RN_no | BI Layer, Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository, Product Offering / Product Design, Product Subscription, Reporting Data Confirmation, Reporting Data Preparation |  | NEO-1210 | In Progress |  | 31 | 5 | 11
Epic | PO: Upgrade WildFly on ExternalServices |  | Market Reporting | Old Fashioned | MR PS Team Team |  | MR PS Team Team: Sprint 5 |  |  | 11. September 2018 |  |  | 24. September 2018 | 8 |  | Upgrade WildFly 12 | RS_RN_no | Product Offering / Product Design |  | NEO-1765 | Open |  | 0 | 0 | 8
Story | Upgrade ExternalServices to WildFly 12 | h1. Description The ExternalServices need to be updated to WildFly 12 | Market Reporting | Old Fashioned | MR PS Team Team |  | MR PS Team Team: Sprint 5 |  |  | 11. September 2018 |  |  | 24. September 2018 | 8 |  | PO: Upgrade WildFly on ExternalServices |  | Product Offering / Product Design |  | NEO-1974 | Open |  | 0 | 0 | 8
Epic | WildFly 12 Upgrade for BI | We have to upgrade to WildFly in version 12. Details related to the upgrade are below https://confluence.gfk.com/display/S2/2018-03-28+WildFly+12+Upgrade Following are the steps / tasks for the upgrade: * Update / Customization puppet script to roll out a WildFly 12 system (DevOps Team) * Test if CLI based Deploy script with WildFly 12 still works (Build Mgmt. Team) * (opt.) test if CLI deployment without server restart process can be resumed in the deploy process (Build Mgmt. Team) * Update / modification of the installer script to customize the local development environment (Build Mgmt. Team + CL Team as consumer) * Raising all previous Java EE applications running on WildFly version 10.1 to run on WildFly 12 through local testing (all domain teams) * Gradual roll out of the upgrade to DEV, TEST, MAINT, DEMO, PROD environment via puppet runs (DevOps Team) | Market Reporting | Old Fashioned | MR BI Team Team, MR PS Team Team | Fotini Gonatidi | MR PS Team Team: Sprint 5 |  |  | 14. August 2018 |  |  | 24. September 2018 | 8 |  | Upgrade WildFly 12 |  | BI Layer |  | NEO-1139 | Open |  | 63 | 5 | 3
Story | Update ST2 installer to have wildfly 12 in local machines and test the upgrade | As part of this story we have to update the ST2 installer so that we can receive an update to wildfly 12 on our local machines. Once the wildfly is upgraded we have to test if the all the below services are working as before * Export Services * Project Services * Load Status Services * Datamart Configuration Services | Market Reporting | Old Fashioned | [9 empty] | 5 |  | WildFly 12 Upgrade for BI |  | BI Layer |  | NEO-2049 | Closed |  | 100 | 5 | 0
Story | BI ¦ Roll out WildFly 12 into different environments | As part of this story we would like to rollout wildfly 12 to all the below environments: * Dev * Test * Maintenance * Production And also check in the development environment if the CLI deployment scripts are still working with the upgraded version or if we have to change them. | Market Reporting | Old Fashioned | MR BI Team Team | Fotini Gonatidi |  |  |  | 14. August 2018 |  |  | 24. September 2018 | 0 |  | WildFly 12 Upgrade for BI | DevOps | BI Layer |  | NEO-2050 | Open |  | 0 | 0 | 0
Sub-Task | Upgrade to wildfly in the development environment |  | Market Reporting | Old Fashioned | MR BI Team Team | Fotini Gonatidi |  |  |  | 14. August 2018 |  |  | 24. September 2018 |  |  | BI ¦ Roll out WildFly 12 into different environments |  | BI Layer |  | NEO-1805 | Open |  | 0 | 0 | 0
Sub-Task | Upgrade to wildfly 12 in the test environment |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | BI ¦ Roll out WildFly 12 into different environments |  | BI Layer |  | NEO-1806 | Open |  | 0 | 0 | 0
Sub-Task | Upgrade to wildfly 12 in the maintenance environment |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | BI ¦ Roll out WildFly 12 into different environments |  | BI Layer |  | NEO-1807 | Open |  | 0 | 0 | 0
Sub-Task | Upgrade to wildfly 12 in the production environment |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | BI ¦ Roll out WildFly 12 into different environments |  | BI Layer |  | NEO-1808 | Open |  | 0 | 0 | 0
Story | To develop Ansible playbook to trigger the wildfly upgrade | As part of this story we would like to develop Ansible playbook so that we can trigger the wildfly upgrade. | Market Reporting | Old Fashioned | MR PS Team Team |  | MR PS Team Team: Sprint 5 |  |  | 11. September 2018 |  |  | 24. September 2018 | 3 |  | WildFly 12 Upgrade for BI |  | BI Layer |  | NEO-2285 | Waiting / Blocked |  | 0 | 0 | 3
Story | To analyze and understand how the scripts needs to be written in Ansible | Understand how the puppet scripts are working to upgrade the wildfly to form a base how the scripts needs to be written in Ansible | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | WildFly 12 Upgrade for BI |  | BI Layer |  | NEO-2282 | Waiting / Blocked |  | 0 | 0 | 0
Epic | WildFly 12 Upgrade for RDC |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Upgrade WildFly 12 |  | Reporting Data Confirmation |  | NEO-2467 | In Progress |  | 0 | 0 | 0
Story | WildFly 12 Upgrade |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | WildFly 12 Upgrade for RDC |  | Reporting Data Confirmation |  | NEO-2468 | Ready for QA |  | 0 | 0 | 0
Feature | BI CI/CD pipeline | As the BI team we want to have a build deployment pipeline for our BI nodes (ApplicationServer, Agent, Listenr) in place. *acceptance criteria * build pipeline created and tested * build process documented *Remark: final build and deployment solution should be completely independent from StarTrack (e.g. Octupus)* | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | BI Layer, Conditioned Feature Backlog |  | NEO-1704 | Open |  | 0 | 0 | 0
Epic | Integrate StarTrack build with NEO deployment pipeline to Octopus | * Extend Jenkins with a job that allows triggering the Octopus deployment via the Octopus CLI → this allows to have single tool to be used for deployments. * Extend the BI Layer aggregator and component deploy pipeline based on groovy scripts to individually deploy BI layer components to any environment from Jenkins → this allows alignment to general groovy based deployment process and to get rid of Octopus | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | BI CI/CD pipeline |  | BI Layer |  | NEO-1778 | Open |  | 0 | 0 | 0
Feature | Make Insight UI development more independent of the data supply | As the Offering team we want to be more independent of the data supplier back-end so that we can also develop the InsightUI application if the Offering specific (e.g. AeroSpike) or any other back-end (e.g. PS) are not available. *Acceptance criteria* * Mocking data solution evaluated and analysed * Solution implemented and tested * Solution reviewed with the lead architect * Solution documented | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | Conditioned Feature Backlog, Product Offering / Product Design |  | NEO-2342 | Open |  | 0 | 0 | 0
Feature | Security - Latest OS and application security patches are applied | As the security department we want to have a Market Reporting solution that is comply with the security GfK standards and constraints. In detail we want to have the latest OS and application security patches are applied on the machines. This feature is based on the following security measures priorization workshop [https://confluence.gfk.com/x/TYOnD]. *Acceptance Criteria: * * all the latest OS and application security patches (IIS, Apache, SQL…) are applied and running | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | BI Layer, Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository, Product Offering / Product Design, Product Subscription, Reporting Data Confirmation, Reporting Data Preparation |  | NEO-1136 | Open |  | 0 | 0 | 0
Feature | Security - Evaluation if applications configured according to application specific secure configuration guidelines | As the security department we want to have a Market Reporting solution that is comply with the security GfK standards and constraints. In detail we want to have that all applications are configured according to the GfK specific secure configuration guidelines. In a first step we want to understand the guidelines and check if our applications meet these guidelines. This feature is based on the following security measures priorization workshop [https://confluence.gfk.com/x/TYOnD]. *Acceptance Criteria: * * configuration guidelines understood * applications checked against the guidelines * needed work to meet the guidelines documented (feature, epic) and communicated | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | BI Layer, Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository, Product Offering / Product Design, Product Subscription, Reporting Data Confirmation, Reporting Data Preparation |  | NEO-2211 | Open |  | 0 | 0 | 0
Feature | Rename Reporting Repository context tables | As the Reporting Repository team we want to rename the exiting context tables to improve the understanding of the data model. The context tables store data that are needed for the versioning functionality of the repository and should therfore have names that reflects this function. *Acceptance Criteria* * tables renamed * documentation adjusted * subsystem fully tested and tests passed *Business Value* 1 | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Sustainable and Maintainable Software Solution | RS_RN_no | Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository |  | NEO-2539 | Open |  | 0 | 0 | 0
Initative | Improve Operational Efficiency | This initiative will include following topics: * Definition of the Features and PCL in the Key Dimension Editor * CDM Enhancements * Provisioning of only reportable data (Confirmed Layer) * Provisioning of client-specific hierarchies * etc. i.e. topics which will enable operation teams to work more efficient. | Market Reporting | Old Fashioned, Gin & Tonic | MR RDC Team Team |  |  |  |  | 14. August 2018 |  |  | 24. September 2018 | [6 empty] | NEO-1322 | Open |  | 0 | 0 | 0
Feature | Provide Feature and Feature Values for KDS | Enabler Feature Load Feature and Feature Values in KDS Objective 4: Provide Feature and Feature Value for KDS via API | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Improve Operational Efficiency | RS_RN_no | Key Dimension Spec / Reporting Repository |  | NEO-2477 | Open |  | 0 | 0 | 0
Epic | Make "Feature Value" available in RR | In order to develop KDS it is essential to have in addition to "Feature"-Dimension the "Feature Values" available in RR. Different to former dimensions the Feature Value is taken over from DWH instead of the MDM-scheme. The Feature-Values have to be tunneld from DWH. For this an API is needed. Only used Feature Values in KDS are made persistent in RR. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Provide Feature and Feature Values for KDS | FeatureValue, KDS, RR | Key Dimension Spec / Reporting Repository |  | NEO-1881 | Open |  | 0 | 0 | 0
Story | Synchronize Feature Values to RR / Provide API to KDS to access Feature Values from ST directly | As an intern. PG responsible and user of KDS I want to select as well as define Feature Values for a Feature. In order to do this the KDS application must have the values accessible. As the number of data sets for Feature Values is huge a Service API, providing access to the corresponding DWH-tables, is needed. Only final selected Feature Values of a KDS instance are finally stored in the RR. Non Funtctional Requirements: performance when loading Feature Values for selection in KDS UI Due to large number of Feature Value records (e.g. X thds To be verified) for numerical Feature Type, no Feature Value from ST must be selectable in KDS. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Make "Feature Value" available in RR |  | Key Dimension Spec / Reporting Repository |  | NEO-1814 | Open |  | 0 | 0 | 0
Story | Provide API from RR to KDS to access Features & Feature Value data from Reporting Repository | Provide an API to KDS application where the API should returned Features and Feature Values data from Reporting Repository based on the Product Group and Country filters that KDS application provided. *Acceptance Criteria: * * The external API for Reporting Repository service already exists and it should work out of the box where system will return features and feature values based on the parameter as below -> hierarchyVersionId * Additional Query Parameters have to be added to the API to provide filters on Product Group and Country so that the correct set of features and feature values could be returned from Reporting Repository to the KDS application. -> productGroupId - integer -> countryId - a collection/array of country Id. * The API should returned only Features and Feature Values that are available in the selected Product Group and Countries. -> For example, if Product Group = PTV and Country = France and Germany; system should only returned Features and Feature Values that are available for these 2 countries. -> For example, if Product Group = PTV and Country = International; system should only returned international Features and Feature Values. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Make "Feature Value" available in RR |  | Key Dimension Spec / Reporting Repository |  | NEO-1916 | Open |  | 0 | 0 | 0
Feature | Establish confirmed layer (excl. UI) to store the rules | The goal is to remove current workaround and to establish confirmed layer to store currently available conf. layer rules (please find description attached). following interactions need to be provided: * request and load available countries and channels shall be created * possibility to define and store the rules for all countries - {color:#ff0000}white list!{color} * communicate white list rules * communicate channels and total/online/offline availabilty per country to be used during the dist unit definition UI will not be provided in the first step. the rules will be defined and stored manually by the developers. Benefit: is an enabler feature to support in future feature with UI. Acceptance Criteria: * Channels and countries are loaded (with internal IDs) * rules for all countries as a white list are defined for all countries which are already rolled out * ruels, channels and availability of the total/online/offline is communicated and is used during dist unit definition. * only reportable channels and pos type can be used in dist unit definition (in country context!) | Market Reporting | Gin & Tonic, Old Fashioned | MR RDC Team Team | [10 empty] | Improve Operational Efficiency | RS_RN_no | Conditioned Feature Backlog, Reporting Data Confirmation |  | NEO-301 | In Progress |  | 0 | 0 | 0
Feature | Stretch Objective: Enable automatic weekly processing of the content changes | At the moment NEO Lite DBs are being updated oncy a month automatically and each week manually, what is causing effort on developers side. There is a need to automate this process, therefor we need to provide a locking mechanism, to stop all data exports(at the moment a manual is being conducted) and to trigger new exports with new information submitted by the users. e.g. of the changes: Add / Change of Retailers, Countries, Product Hierarchies, Dist Unit definitions. Benefit: * reduce manual efforts * increase dev efficiency Acceptance Criteria: * automatic process is triggered once a week * all newly submitted changes are available in insight | Market Reporting | Gin & Tonic, Old Fashioned | [11 empty] | Improve Operational Efficiency | RS_RN_yes | BI Layer, Conditioned Feature Backlog, Product Subscription, Reporting Data Preparation |  | NEO-1519 | In Progress |  | 0 | 0 | 0
Feature | Stretch Objective: Conduct technical preparation for KDS | Scope limitation: this is an enbler feature and will be done as preparation to establish KDS. * set up project * request and set up DB * prepare widgets and controls to start UI development ------ Currently we have a workaround in place, which enalbe definition of the PCL and feature in GSE using LOBs. In future we want to remove such dependency and provide a UI (application) which will enable such specifications. Benefit: * remove manual workaround * enable savings * improve dev efficiency Acceptance Criteria: * provide a automatical proposal for PCL ranges in local currency per country, per PG(Base PGS? RPG?) * provide a possibility for the user to modify proposal (incl. use of ) * provide a possibility to define 4 key features and belonging feature values * for numerical features support ranges, single values or GroupValues * for non-numerical features support single values and GroupValues * check if each PG has a PCL defined (PCL definition is mandatory, featue and feature values definition is in general optional) * reflect the PCL and 4 key feature definitions in the NL4RS | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Improve Operational Efficiency | RS_RN_no | Conditioned Feature Backlog, Key Dimension Spec / Reporting Repository, Reporting Data Preparation |  | NEO-1950 | Open |  | 0 | 0 | 0
Epic | Enabler for KDS-Development | Background :* Currently the definition of PCL and features is made in GSE by using LOBs. A LOB is created for each Reporting PG and country. In order to avoid this GSE-dependency and source of errors (due to one time definition without having an automated update process) a new application, called KDS will be developed. The full replacement requests the definition of a set of features for PS PG as a global standard and national exceptions, the definition of its corresponding Feature Values (auto proposal functionality) as well as PCLs for a PS PG on a national level/local currencies (auto proposal functionality). The Feature NEO-283 will be broken down, based on the requirements placed by Stakeholders ([~aakais], [~iacris], [~Tristan.Irwin]) as following: -> Define a set of feature for a PS PG as a global standard. -> Define feature value for the global standard feature (auto proposal requested). -> Define PCL for a PS PG for an intern. currency (global standard like Euro, US Dollar, British Pound) -> Define country-specific set of features -> Define country-specific feature values for country-specific feature. -> Define country-specific PCL for PS PG (auto proposal requested). To be done [~cnkrae]: add all the other identified epics. A "Global Standard" can be copied and adapted to national needs (one or multiple country selection is possible). This EPIC is the pre-condition for developing KDS functionality. Several technical preparations have to be done first. Benefits : Decoupling of GSE. less errors in operations as well as updated source data due to automated synch process in case of data changes. *Acceptance criteria : * * Architecture Design - documented in Confluence * Tech Design for KDS DB * DB created in Oracle * KDS-developing project created * New URL for KDS are set up * Extent RR Region Dimension by local currencies and Source ID. Risk: : NA | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Stretch Objective: Conduct technical preparation for KDS |  | Key Dimension Spec / Reporting Repository |  | NEO-1782 | Open |  | 0 | 0 | 0
Story | SPIKE KDS DB Design |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Enabler for KDS-Development |  | Key Dimension Spec / Reporting Repository |  | NEO-1763 | Open |  | 0 | 0 | 0
Story | Design UI Widget and CSS for KDS Project | Before starting the implementation for KDS project, the UI widget and CSS for KDS have to be ready to ensure standardized UI being used across the application. As a developer, I would like to prepare and design the KDS UI widget and CSS for KDS project as this is a new project and new user interface, which has a different look and feel from Reporting Repository. Expected Result: The KDS UI widget and css is available and check-in to the KDS project and ready to be used for development. Error Handling *Acceptance Criterion* * (non-functional requirement) The design must correspond to the design of RR UI - new UI widgets are needed for KDS - however whenever possible - existing ones from RR must be used. * Based on the mockup of KDS project, design and create the UI widget and CSS and check-in to Master branch for future development usage. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Enabler for KDS-Development | KDS | Key Dimension Spec / Reporting Repository |  | NEO-1833 | Open |  | 0 | 0 | 0
Story | Create KDS database in Oracle |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Enabler for KDS-Development |  | Key Dimension Spec / Reporting Repository |  | NEO-1764 | Open |  | 0 | 0 | 0
Story | Create KDS Project | As a developer, I would like to create the KDS project with the necessary classes and library setup in the .NET project. Pre-Condition Spike for KDS has to be completed before the implementation of this user story: US-01: SPIKE: Architecture Design for new KDS Application Acceptance Criteria: * Create and setup the KDS project; classes, library, etc based on the technical design documented on confluence. (link to be added later) * The service component should provides HTTP interface to all Reporting sub-domains as well as to the KDS web application. * Create the GIT Repository / Jenkins project (the solution and deployment units) for KDS * Aggregator * CCR-Deploy-Config * IIS Hosting * ADFS Configuration | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Enabler for KDS-Development |  | Key Dimension Spec / Reporting Repository |  | NEO-1766 | Open |  | 0 | 0 | 0
Story | Set-up new URL for KDS with ADFS |  | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Enabler for KDS-Development |  | Key Dimension Spec / Reporting Repository |  | NEO-1767 | Open |  | 0 | 0 | 0
Epic | Finalize "Region" Dimension in RR | For KDS property definition "PCL" the currency is needed. Local currencies are an attribute of the ADM_COUNTRY table (see screenshot) - to be checked if Country-dimension from MDM contains this info as well). !CurrencyInfo.png¦thumbnail! | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Stretch Objective: Conduct technical preparation for KDS |  | Key Dimension Spec / Reporting Repository |  | NEO-1884 | Open |  | 0 | 0 | 0
Story | Complete dimension "Region" in RR | As a MR (Sub)Domain I want to get all region-relevant data from RR. AC: * Source element IDs provided * Country currencies are available (local currencies are an attribute of the ADM_COUNTRY table (see screenshot) - to be checked if Country-dimension from MDM contains this info as well). !CurrencyInfo.png¦thumbnail! (relevant for PS and CL) | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Finalize "Region" Dimension in RR | RDC, RR | Key Dimension Spec / Reporting Repository |  | NEO-1770 | Open |  | 0 | 0 | 0
Feature | Communicate and apply CL rules | the goal is to integrate confirmed layer with product subscription, Thereby commnucating the rules defined in RDC to PS and appling the rules by preprocessing component during data load into AS. Benefit: ensure quality and security reduce manual effort on dev side Business Value: 3 Acceptance Criteria: Add the rules manually to the database (no UI) Save rules manually (directly) to the database of the current countries. PS shall use confirmed layer interface. Confirmed layer shall provide NCDM the defined rules for the requested country. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Improve Operational Efficiency | RS_RN_no | Product Subscription, Reporting Data Confirmation |  | NEO-2460 | Open |  | 0 | 0 | 0
Feature | Enable Definition of CL rules via UI | The goal is to provide a UI to enable operation team to define CL rules. Benefit: Ensure quality and security hand over CL definition into Ops Teams hands, thereby reducing effort on dev side Business Value: 4 Acceptance Criteria: implement UI to define CL rules - as discussed and documented in mock ups. | Market Reporting | Old Fashioned | [5 empty] | 14. August 2018 |  |  | 24. September 2018 |  |  | Improve Operational Efficiency | RS_RN_yes | Reporting Data Confirmation |  | NEO-2461 | Open |  | 0 | 0 | 0
Epic | RDP: Other Supporting Improvement/Tasks/Bugs for "Old Fashioned" Release | These are Supporting Improvement/Tasks/Bugs current Release being done by RDP Team. These may not be directly related to any feature/Epics but are necessary to do it. | Market Reporting | Old Fashioned | MR BI Team Team, MR PS Team Team | Fotini Gonatidi | MR PS Team Team: Sprint 3, MR BI Team Team: Sprint 3 |  |  | 14. August 2018 |  |  | 27. August 2018 | 6 |  |  |  | Reporting Data Preparation |  | NEO-2588 | Open |  | 0 | 0 | 6
Story | RDP : setup/prepare additional server/DM's [DCEW-APRTPEN15 ] | As a DevOp i need the DataMart server be configured equal to the Production DataMarts * setup DCEW-APRTPEN15 server/DM +Dependency:+ * Database Users have to be added by GroupIT DBA +Acceptance criteria:+ * User Add Sql Script is installed on Server * RDP Team aproved that System is configured correct | Market Reporting | Old Fashioned | MR PS Team Team |  | MR PS Team Team: Sprint 3 |  |  | 14. August 2018 |  |  | 27. August 2018 | 3 |  | RDP: Other Supporting Improvement/Tasks/Bugs for "Old Fashioned" Release |  | Reporting Data Preparation |  | NEO-2060 | In Progress |  | 0 | 0 | 3
Story | RDP : setup/prepare additional server/DM's [DCEW-APRTPEN14] | As a DevOp i need the DataMart server be configured equal to the Production DataMarts * setup DCEW-APRTPEN14 server/DM +Dependency:+ * Database Users have to be added by GroupIT DBA +Acceptance criteria:+ * User Add Sql Script is installed on Server * RDP Team aproved that System is configured correct | Market Reporting | Old Fashioned | MR BI Team Team | Fotini Gonatidi | MR BI Team Team: Sprint 3 |  |  | 14. August 2018 |  |  | 27. August 2018 | 3 |  | RDP: Other Supporting Improvement/Tasks/Bugs for "Old Fashioned" Release |  | Reporting Data Preparation |  | NEO-2062 | In Progress |  | 0 | 0 | 3
Epic | Better CI/CD Process Longlist | This epics constrains some Technical user stories which RDP team feel should be implemented in order to facilitate the efficient development and deployment process which indirectly will help in stable/improved process/environments. *+Value:+* : Improved and efficient RDP development and deployment platform/environments. This has been prioritized for Old fashioned PI and needs to be aligned with PO's (Once all the User stories are groomed). | Market Reporting | Old Fashioned | MR RDP Team Team |  |  |  |  | 14. August 2018 |  |  | 24. September 2018 |  |  |  |  | Reporting Data Preparation |  | NEO-376 | Open |  | 0 | 0 | 0
Epic | Improve CI/CD Process for Old Fashioned | This epics constrains some Technical user stories which RDP team feel should be implemented in order to facilitate the efficient development and deployment process which indirectly will help in stable/improved process/environments. *+Value:+* : Improved and efficient RDP development and deployment platform/environments. | Market Reporting | Old Fashioned | MR RDP Team Team | [12 empty] | Reporting Data Preparation |  | NEO-2554 | Open |  | 0 | 0 | 0